## Title Page
Group Number: |  | 15
Group Name: |  | Group 15
Group Members:
#1: | Zack Clements
#2: | Afif Mujibur-Rahman
#3: | Kyle Prindle
#4: | Mackenzie Teaster
#5: | Jake Thakur

## Product Backlog(To-do)
Group Number | 15
Project Name: | Campus Crowd
Description: | Interactive map that allows users to see what parts of campus are busiest at what times, allowing students to plan trips to campus accordingly. | PRODUCT BACKLOG (TO-DO)
Team Members | Zack Clements, Afif Mujipur-Rahman, Mackenzie Teaster, Kyle Prindle, Jake Thakur
Story # | Card Front | Card Back | Sprint Number | Priority | Assigned To | Comments | Estimated Points | Estimated Hours | Estimated Velocity | Actual Velocity
| As a <user who wants this functionality> I need a <what the user wants> so that <why the user wants it>. | Acceptance Criteria <what the user should be able to do with the functionality> | [6 empty] | (Estimated Points / Estimated Hours) | (Estimated Points / Actual Hours)
1 | As a moderator, I would like a way to interpret wifi usage data, so that I can tell where it is busy on campus | Read locations from highest - lowest concentration of wifi usage | Sprint 2 | 1st |  |  | 7 | 20 | 2022-07-20
2 | As a user, I would like to see a heat map of campus, so that I can know where it is busy on campus | View a map generated by the wifi usage data | Sprint 2 | 2nd |  |  | 5 | 10 | 2022-05-10
3 | As a moderator, I would like the heat map to be interactive, so that users can find locations easily | Tap, zoom on, drag the map | Sprint 2 | 4th |  |  | 4 | 5 | 2022-04-05
4 | As a user, I would like the app to have an aesthetic and minimalist design, so that I can navigate it easily | Web Standards and Usability Guidelines from https://webstandards.hhs.gov/guidelines/ are implemented accurately. | Sprint 2 | 5th |  |  | 2 | 2 | 1
5 | As a user, I would like the app to be easily accessible whenever needed with the latest update. | Frequently updated heatmap (every minute or two) | Sprint 2 | 3rd |  |  | 5 | 10 | 2022-05-10
6 | As a user with vision loss, I would like the app to be accessible without a mouse | Access core product components with only a keyboard | Sprint 3 | 7th |  |  | 5 | 10 | 2022-05-10
7 | As a user with disabilities, I would like the app to stay up-to-date with current accessibility standards | Ensure that the WCAG 2 is being followed and implemented as needed. https://www.w3.org/WAI/standards-guidelines/wcag/ | Sprint 3 | 8th |  |  | 7 | 20 | 2022-07-20
8 | As a moderator, I would like to be able to predict future hotspots based on upcoming events | Schedule that can show when crowds may be larger based on events | Sprint 3 | 6th |  |  | 4 | 5 | 2022-04-05
9 | As a user, I would like to see how busy certain places are throughout the day. | When a building is selected, show a bar graph of wifi use for the day in that building. | Sprint 3 | 9th |  |  | 4 | 5 | 2022-04-05
10 | As a user, allow me to access this information without creating an account | Allow users to access the map without logging in or creating an account on the website | Sprint 3 | 10th |  |  | 1 | 1 | 1
11 | As a user, I would like to see locations on campus that I've selected. | Allow users to pin locations on the map for easy viewing | Sprint 3 | 11th |  |  | 3 | 4 | 2022-03-04
12 | As a user, I would like to look back at how busy campus was on a previous day. | Allow users to select specific dates to view. | Sprint 3 | 12th |  |  | 5 | 10 | 2022-05-10

## DONE (post St.1 and St.2)
Group Number | 15
Project Name: | Campus Crowd
Description:
Team Members
[6 empty] | Sprint 1 |  |  |  | Sprint 2
Story # | Card Front | Card Back | Sprint Number | Priority* | Estimated Points | Estimated Hours | Actual Hours | Estimated Velocity | Actual Velocity | Estimated Hours | Actual Hours | Estimated Velocity | Actual Velocity | Assigned To | Comments
| As a <user who wants this functionality> I need a <what the user wants> so that <why the user wants it>. | Acceptance Criteria <what the user should be able to do with the functionality> | [5 empty] | (Estimated Points / Estimated Hours) | (Estimated Points / Actual Hours) |  |  | (Estimated Points / Estimated Hours) | (Estimated Points / Actual Hours)
1
2
3
4
5
6
7
8
9
10
11
12
* It might not conform to the Sprint numbers here, but remains same as your group decided in the initial sprint

## Doing
Group Number | 15
Project Name: | Campus Crowd
Description: | DOING
Team Members
Story # | Card Front | Card Back | Estimated Points | Estimated Hours | Actual Hours | Estimated Velocity | Actual Velocity | Sprint Number | Priority | Assigned To | Comments
1 | As a moderator, I would like a way to interpret wifi usage data, so that I can tell where it is busy on campus | Read locations from highest - lowest concentration of wifi usage | 7 |  |  | (Estimated Points / Estimated Hours) | (Estimated Points / Actual Hours) | Sprint 1
ST - 4
ST - 5
ST - 6
ST - 7
ST - 8
ST - 9
ST - 10
ST - 11
ST - 12

## Story Point Key
Story Point Key